Device Diagnostics & Trade-In

SaaS Platform

Development Roadmap & Implementation Plan

August 2026

Prepared from architecture specification: CLAUDE.md

# 1. Executive Summary

This document translates a completed design and architecture phase into an actionable development plan. The platform consists of three surfaces (a React Native mobile app, a tenant admin web portal, and a Master Admin console) built on a multi-tenant SaaS backend, serving the mobile device trade-in and refurbishment industry.

What exists today: ~20 TypeScript modules defining all types, interfaces, and business logic; 17 mobile app screens as interactive HTML mockups; 12+ admin portal pages; a Master Console; consumer-facing flows; and a comprehensive architecture document (CLAUDE.md). None of it runs — there is no backend, no database, no deployed frontend.

What this roadmap covers: 8 development sprints over approximately 16–20 weeks, taking the project from architecture artifacts to a deployable MVP, then through external integrations to a production-ready platform.

# 2. Architecture Overview

## 2.1  Three surfaces

•  React Native mobile app (iOS + Android) — 17-step technician flow: login, profile scan, license check, device eligibility, identity capture, diagnostics, cosmetic grading, trade-in offer, completion

•  Tenant admin web portal (React/Next.js) — Dashboard, Reports, Devices, Test Profiles, Compliance, Disputes, Billing, Team, Activity Log, Settings

•  Master Admin console — cross-tenant management, platform analytics, revenue/billing, tenant provisioning

## 2.2  Multi-tenant model

•  tenant.ts is the top-level entity — one Tenant per paying company

•  CustomerProfile belongs WITHIN a tenant (not AS one) — a tenant can have multiple profiles

•  License bills at the tenant level, not per-profile

•  Portal has role-based auth: master_admin (unscoped), tenant_admin, tenant_staff (locked to one tenant)

•  PINs are unique per-tenant, not globally — QR codes encode tenantId:pin together

## 2.3  Key resolved decisions

•  Redo after report generation: same reportId with revision suffix (-R1, -R2)

•  Unrecognized PIN: blocks the session, never falls back to a default profile

•  Technician login: separate from customer PIN, session-level (one per shift)

•  Data retention: keep forever, no automatic purge (manual deletion path noted for GDPR/CCPA)

•  Device eligibility: hard gate — blacklisted/locked devices never silently proceed into diagnostics

# 3. Module Inventory

Every module below has complete TypeScript types, interfaces, and logic functions. The "Status" column indicates what remains before each module is production-ready.

| Module | Purpose | Status |
| --- | --- | --- |
| tenant.ts | Top-level tenant entity, CRUD | Logic complete, needs DB persistence + API endpoints |
| portalAuth.ts | Portal login, roles, tenant view switching | Logic complete, needs real auth (JWT/session), DB |
| technicianAuth.ts | Lightweight badge/code login for mobile app | Logic complete, needs API endpoint |
| customerProfile.ts | Profile CRUD, QR generation/parsing, PIN resolution | Logic complete, needs CRUD API endpoints, DB |
| licensing.ts | License enforcement, seat tracking, provisioning | Logic complete, needs DB + Stripe integration for billing |
| invoicing.ts | Invoice line items, overage calculation | Logic complete, needs Stripe Billing or equivalent |
| testPlanRegistry.remote.ts | 98 remote-mode TestPlanKey to ReturnKey mappings | Complete data — needs API to serve to mobile app |
| testSession.ts | Session management, redo logic, revision tracking | Logic complete, needs DB persistence |
| cosmeticInspection.ts | 6-angle capture, hosted CV inference, grade computation | Needs a trained model deployed behind an API |
| datasetCollection.ts | Labeled training example capture for model improvement | Logic complete, needs storage backend for images |
| reportRenderer.ts | HTML-to-PDF report with wipe cert, routing badge, QR | Logic complete, works with react-native-html-to-pdf |
| deviceVerification.ts | Activation lock + IMEI blacklist gate | Needs GSMA Device Check or CellDe signup |
| tradeInQuote.ts | Grade-based valuation, deductions, payout tracking | Logic complete, needs real pricing feed |
| marketPriceData.ts | Seed price tables (US, India, Australia) | Placeholder data — needs real market feed |
| marketPriceUpload.ts | Excel upload parser for admin-maintained pricing | Logic complete, needs file upload API |
| fraudDetection.ts | Parts authenticity + serial mismatch detection | Serial mismatch works; parts CV needs training data |
| deviceRouting.ts | Post-grading resale/repair/parts/recycle/hold routing | Logic complete |
| dataWipe.ts | NIST 800-88 certified erasure records | Logic complete |
| batchSession.ts | Bulk lot intake, deduped serial scanning | Logic complete, needs DB |
| offlineSync.ts | Queue-and-retry for network-dependent operations | Logic complete, needs local storage integration |
| notifications.ts | SMS/email templates per consumer-tracker stage | Templates complete, needs Twilio/SendGrid |
| shippingLogistics.ts | Inbound label + tracking data model | Data model only, needs EasyPost/Shippo |
| kycVerification.ts | Payout threshold gate for identity verification | Logic only, needs Persona/Jumio/Onfido |
| warrantyTracking.ts | Post-sale claims linked to original report | Logic complete, needs DB + portal CRUD |
| marketplaceListing.ts | Auto-generates resale listing from report data | Logic complete |
| adminActivityLog.ts | Central audit trail, wired into 7 modules | Logic complete, needs DB persistence |

# 4. Sprint Plan

Two-week sprints. Earlier sprints are tighter in scope because they establish the foundation everything else depends on — later sprints are broader because they build on a working system.

## Phase 1: Foundation (Sprints 1–3)

| Sprint | Deliverables | Dependencies | Duration |
| --- | --- | --- | --- |
| S1 | Database schema (PostgreSQL): tenants, profiles, licenses, technicians, reports, activity_log. API skeleton: Express/Fastify + TypeORM/Prisma. Auth: portal login (JWT), technician badge login. Multi-tenant query scoping (every query filtered by tenantId). | None — this is the starting point | 2 weeks |
| S2 | Tenant CRUD API + Master Console backend. License CRUD + enforcement API. Profile CRUD + QR generation endpoint. Admin activity log persistence (every write operation logs). | Sprint 1 (DB + auth) | 2 weeks |
| S3 | React Native project scaffold. Navigation (React Navigation) for the 17-step flow. Technician login screen (real API call). Profile QR scan (ML Kit barcode). License check gate (real API call). | Sprint 2 (APIs exist to call) | 2 weeks |

## Phase 2: Core Mobile App (Sprints 4–5)

| Sprint | Deliverables | Dependencies | Duration |
| --- | --- | --- | --- |
| S4 | Device identity capture: barcode scan, OCR fallback, manual entry, technician confirmation. Make/model auto-detection. IMEI validation (15-digit format check). Session management + report creation API. | Sprint 3 (mobile scaffold) | 2 weeks |
| S5 | All diagnostic tests: battery, sensors, storage, camera, mic, speaker, ports. Cosmetic grading: 6-angle guided photo capture + manual grade entry (CV inference deferred to S7). Country of origin capture. Results screen with 'Redo Flagged Tests' bulk action. PDF report generation (react-native-html-to-pdf). | Sprint 4 (identity capture) | 2 weeks |

## Phase 3: Portal + Consumer Flows (Sprint 6)

| Sprint | Deliverables | Dependencies | Duration |
| --- | --- | --- | --- |
| S6 | Tenant admin portal (React/Next.js): Dashboard, Reports list + detail, Devices + device history, Test Profiles editor, Team page, Billing, Activity Log, Settings. Consumer tracker: status page, offer accept/decline, payout method selection, dispute submission form. Admin dispute queue with resolve actions. | Sprint 5 (reports exist in DB) | 2 weeks |

## Phase 4: External Integrations (Sprints 7–8)

| Sprint | Deliverables | Dependencies | Duration |
| --- | --- | --- | --- |
| S7 | Device verification: GSMA Device Check or CellDe integration (activation lock + IMEI blacklist). Cosmetic CV: deploy initial model (public dataset, ~2k images) behind inference API, wire into mobile capture flow. Trade-in quote engine: wire market pricing upload + quote computation + offer screen. | Sprint 5 (mobile tests complete) + vendor signup | 2 weeks |
| S8 | Stripe Billing: wire invoicing.ts to real charges, subscription management, payment history. Notifications: Twilio (SMS) + SendGrid (email), triggered per consumer-tracker stage. Shipping: EasyPost/Shippo label generation + tracking webhooks. KYC: Persona/Jumio integration, gated before payout processing. Batch intake mobile UI wired to real API. | Sprint 7 + all vendor signups | 2 weeks |

# 5. Critical Path & Blocking Dependencies

## 5.1  What blocks what

•  Everything blocks on Sprint 1 (database + auth) — nothing real can happen without it

•  The mobile app (S3–S5) blocks on APIs existing (S2)

•  The web portal (S6) blocks on reports existing in the database (S5)

•  External integrations (S7–S8) block on vendor signups, which should start during S1–S2 so credentials are ready when code is

## 5.2  Vendor signups to start immediately

These take days to weeks for account approval, API key provisioning, and sandbox access. Start the signup process during Sprint 1, not Sprint 7:

•  GSMA Device Check (devicecheck.gsma.com) — or CellDe as a tier-2 alternative

•  Stripe (stripe.com) — Billing product specifically for metered/subscription

•  Twilio (twilio.com) — SMS

•  SendGrid (sendgrid.com) or Postmark — transactional email

•  EasyPost (easypost.com) or Shippo — shipping labels + tracking

•  Persona (withpersona.com) or Jumio — KYC/identity verification

## 5.3  Mobile app store submissions

Apple App Store review typically takes 1–3 days; Google Play is faster but both require developer accounts set up in advance. Start the Apple Developer Program enrollment ($99/year) and Google Play Console ($25 one-time) during Sprint 1. TestFlight (iOS) and internal testing tracks (Android) should be set up by Sprint 3 for ongoing QA.

# 6. Suggested Team Structure

•  1 backend engineer — API, database, multi-tenant scoping, external integrations

•  1 React Native engineer — mobile app, all 17 screens, camera/barcode/OCR, offline sync

•  1 frontend engineer — admin portal (React/Next.js), Master Console, consumer-facing pages

•  1 ML engineer (part-time / contract) — cosmetic grading model: initial training on public dataset, inference API deployment, retraining pipeline from datasetCollection.ts

•  1 QA engineer — manual testing initially, then automated test suite

A 3-person team (one person covering backend + integrations, one mobile, one web) is the realistic minimum. The ML work can be contracted out or deferred — the mobile app works with manual cosmetic grading (technician enters grade directly) until the model is ready.

# 7. Risk Register

•  GSMA Device Check approval timeline is unknown — have CellDe as a fallback vendor ready

•  iOS battery health cannot be read programmatically — manual entry (from Settings screen) is the designed solution, but users may find this friction unacceptable at scale. OCR of a Settings screenshot is the mitigation, already designed

•  Cosmetic grading model accuracy on ~2k public images will be low — ship with manual grading as the primary path and treat the model as a suggestion, not a gate (this is already the design)

•  Market pricing data is placeholder-quality — the Excel upload feature exists specifically to let admins maintain real pricing without a code change, but someone still needs to maintain it

•  Multi-tenant data isolation is currently visual only (tenant badges on every page) — Sprint 1 must implement query-level scoping before any real tenant data enters the system

•  No automated tests exist — risk of regressions increases with each sprint. Start writing tests in Sprint 2 alongside the first API endpoints

# 8. Not in Scope for MVP

These were discussed during architecture but explicitly deferred:

•  Self-service tenant onboarding (new companies signing themselves up — MVP uses manual provisioning by master admin)

•  Counterfeit-parts detection via CV (no public training data exists — ships as a manual technician checklist)

•  Real-time market pricing feed (MVP uses admin-uploaded Excel; a live API integration is a post-MVP feature)

•  GDPR/CCPA automated deletion workflow (manual process documented in Settings, no self-service)

•  Marketplace listing auto-publishing (module generates listing content; actually posting to eBay/Swappa/etc. is a post-MVP integration)

•  New Zealand, Southeast Asia, and Japan pricing (no data found — add when real per-market data is available)

# 9. Deliverable Inventory

All files from the architecture phase are available in the project repository:

## 9.1  TypeScript modules (~20 files)

tenant.ts, portalAuth.ts, technicianAuth.ts, customerProfile.ts, licensing.ts, invoicing.ts, testPlanRegistry.remote.ts, testSession.ts, cosmeticInspection.ts, datasetCollection.ts, reportRenderer.ts, deviceVerification.ts, tradeInQuote.ts, marketPriceData.ts, marketPriceUpload.ts, fraudDetection.ts, deviceRouting.ts, dataWipe.ts, batchSession.ts, offlineSync.ts, notifications.ts, shippingLogistics.ts, kycVerification.ts, warrantyTracking.ts, marketplaceListing.ts, adminActivityLog.ts

## 9.2  UI mockups (HTML)

Mobile app: ui_journey_premium.html (17 screens), mobile_batch_intake.html (3 screens)

Consumer-facing: consumer_tracker.html, consumer_payout.html, consumer_dispute.html

Admin portal: admin_portal.html (dashboard), admin_portal_detail.html, admin_portal_devices.html, admin_portal_device_history.html, admin_portal_profiles.html, admin_portal_compliance.html, admin_portal_disputes.html, admin_portal_billing.html, admin_portal_team.html, admin_portal_settings.html, admin_portal_activity_log.html

Master admin: master_console.html, portal_login.html

## 9.3  Supporting documents

CLAUDE.md — comprehensive architecture reference (the canonical document for anyone picking up this codebase)

cosmetic_grading_dataset_plan.md — public dataset sources + collection framework

market_pricing_template.xlsx — uploadable pricing template with US/India/Australia seed data